## Value per feature
Feature | Centre | Input from the customer | What the agent does | What a human does | Output | What the agent remembers | Human hours by hand (estimate) | Human hours with Signal Harbor | Hours saved | How the hours were worked out | What the company gains | Built today?
1. Company profile (Bring what you have) | Intent | Strategy or investment policy, last 2-3 committee packs, people list, systems list, classification policy, known issues (Customer standard inputs 1-9) | Nira reads every file into the profile: people, systems, pains, restricted areas, measures in the packs; marks each cell guessed with its source; lists what is missing | Organiser drops files into nine tiles; confirms or corrects the guesses | A company profile with provenance (stated, guessed, unknown); readiness bar | Company memory: systems, teams, recurring pains, who owns what. Next cycle starts prefilled | 32 | 0.5 |  | Manual: an analyst reads and summarises the documents (3-5 days). With the product: 10 min upload (measured) plus about 20 min confirming | One place where the company's own facts live, with sources; nothing re-asked later | Built
2. One interview per person | Intent | 10-15 key people; their time | North (leaders) and Lens (owners) run a 5-15 min interview, skip questions the documents already answer, write answers into the profile and as draft cards | Each person answers by text or voice | Interview answers in the profile; draft cards for the wall | Person memory per agent: priorities, pains, open threads; used in that person's next conversation | 30 | 2.5 |  | Manual: a consultant interviews 10 people for 1 hour and writes notes for 1 hour (20 h) plus the people's 10 h. With the product: median 11 min per person (measured) | Every voice captured the same way, including anonymous ones; no consultant notes to chase | Built (old look)
3. The wall (Think unfiltered) | Intent | Topic, purpose, days open; the participants | North drafts each person's cards from their interview and documents; suggests up to three cards per lane; groups the wall into clusters at close | Organiser starts the wall and moves the stages; each person confirms or adds cards (about 5 min) | A frozen wall of cards in four lanes; clusters ready for Define | Company memory: recurring themes across walls; North's suggestions improve per company | 32 | 1.5 |  | Manual: plan a workshop (8 h), run it with 8 people for 2 h (16 h), write it up (8 h). With the product: organiser 30 min, each person 5 min | Ideas from people who would not speak in a meeting; grouping done in seconds | Built; invite and stage bar to build
4. Define and the charter | Intent | The clusters; the committee's judgement | Lens proposes a shelf for each cluster and the measures behind it; drafts the charter with 'so that' lines; Nira chases signatures | Committee of 8 decides the shelves in one 90-min session (about 20 decisions); sponsor signs the charter | Signed charter: problems with priority, pains, signals, levers, who took part | Company memory: past priorities and why; Lens proposes shelves closer to past decisions | 28 | 12.5 |  | Manual: prepare options (8 h), committee 90 min x 8 (12 h), write the charter (8 h). With the product: the same 90-min session plus a 30-min signature | A signed, traceable statement of what the business wants to know | Built; charter screen to re-skin
5. Baseline (definitions and governance) | Intent | Glossary, KPI definitions, data dictionary, SOPs, classification policy (if they exist) | Lens drafts every measure: business and technical definition, owners, classification, who may see, process map, glossary; asks owners only the gaps by link | Each owner confirms or corrects their measures (about 10 min each); sponsor signs the baseline | Signed baseline: per measure definitions, owners, personal data, who may see; catalogue; glossary; known risks | Lens remembers each owner's corrections; next quarter's definitions come pre-agreed | 80 | 5 |  | Manual: 20 measures x 3 h of analyst work (60 h) plus 1 h per owner (20 h). With the product: 10 min per owner and 1 h of review and signing | A governed catalogue the company owns and reuses for every report and audit | Built (old look); new screen to build
6. Moment of truth (trial and plan) | Intent | One recent period of sample data per key source; the reported figures in the packs | Lens profiles each file, recomputes each measure, compares with the reported figure, proposes quality rules, scores sources, drafts the phased plan | Source owners upload a file by link (about 10 min each); sponsor and head of data read and sign the plan (30 min) | Signed phased plan: trial per measure (match, gap, not yet), risks, bands Now / Next / Later | Lens remembers known gaps and quality rules per source; the next trial starts from them | 60 | 2.5 |  | Manual: collect samples, profile and reconcile 20 measures against the pack (40-80 h). With the product: uploads plus a 30-min review | Proof, before any build money is spent, of which numbers can be trusted | Built
7. Blueprint | Build | Five environment answers; the signed baseline and plan | Architect drafts the data model (facts, dimensions, keys), lineage per measure, rules, access per mart, schedule; draws the diagram | Head of data reviews and signs (about 1 h) | Signed blueprint.json and its diagram | Architect remembers the company's naming and modelling choices | 40 | 1.5 |  | Manual: a data architect for about a week. With the product: 20 min of answers plus 1 h of review | A design traceable to every agreed measure | Environment built; blueprint to build
8. Pipelines and loading | Build | Files arriving where the environment check says | Builder generates one pipeline contract and its code per source; runs bronze, silver, gold into the company's DuckDB; logs every run | Admin clicks Run now the first time; owners fix a source when a check fails | A warehouse in the company's own space; a run log | The runner remembers each source's usual volume and arrival time | 160 | 4 |  | Manual: data engineers for 3-5 weeks for 6-8 sources. With the product: a few hours of review | Working data without hiring a data team | Warehouse core built; rest to build
9. Prove and release | Build | The loaded data; the reported figures | Prover recomputes each measure for each reported period and explains any gap | Owners accept or explain gaps; sponsor signs the release | Release-ready measures with evidence | Accepted gaps are remembered, so they are not raised again | 40 | 2 |  | Manual: reconciliation by analysts (1 week). With the product: review and sign | Numbers the committee can trust, with the evidence attached | To build
10. Ops (the Watcher) | Build | Nothing new | Watcher checks each day for late files, failed checks and odd values; tells the owner what to do | Owner acts on an alert | A daily status list | Normal ranges per measure learnt over time | 4 | 0.5 |  | Per week. Manual: someone checks the loads each week (4 h). With the product: act on alerts only | Problems found before the committee meets, not during it | To build
11. Feeds | Consume | Nothing new | Builds each measure's latest value and trend from the warehouse; respects who may see | Read; ask a question | A live view of the agreed measures | Which measures each person looks at | 40 | 0.5 |  | Manual: build a dashboard (1 week). With the product: it appears from the governed measures | One version of the numbers for everyone | To build
12. Market forces | Consume | Optional licensed feeds; internet switched on per company | Brings industry briefs and signals next to the company's own measures, marked as outside material | Read | Market context next to each measure | Which signals mattered to this company | 4 | 0.25 |  | Per week. Manual: an analyst gathers market news (4 h). With the product: read the brief | Context without a research subscription per person | To build
13. What-if | Consume | A driver and a change | Follows the company graph to the measures the driver moves and recalculates them | Choose the driver and the change; decide | Which measures move and by how much | Past scenarios and their outcomes | 8 | 0.5 |  | Per scenario. Manual: an analyst models it in Excel (1 day). With the product: minutes | Faster decisions with the path shown | To build
14. Agent long-term memory | All | Nothing new: it comes from the conversations | Each agent summarises every conversation into person memory and a de-personalised company memory; compacts as it grows; never keeps anonymous notes, restricted areas or figures | A person can read, correct or delete what an agent remembers; the admin reviews company memory | Agents that know the company better each cycle | This is the memory | 0 | 0 |  | Saving shows in the second cycle: interviews shorter, definitions pre-agreed, Define faster | The second quarter costs a fraction of the first | To build (designed: MEM-1, MEM-2)

## Savings
Part of the journey | Human hours by hand | Human hours with Signal Harbor | Hours saved | Share of the work done by agents
Intent centre, one cycle (features 1-6)
Build centre, first build (features 7-9)
Running each week (Ops and Market forces)
Consume set-up (Feeds) and one What-if
First cycle: Intent, Build and Consume set-up
All hour figures are estimates to check with the first customer. Measured so far: 10 min to upload the files; interview median 11 min. The by-hand figures assume one analyst or consultant doing the work with the company's people, for about 20 measures and 6-8 sources.
The second cycle should cost less again because the agents remember the company (feature 14). That saving will be measured, not assumed.

## Build order
Agent | Feature | Task | Files it alone owns | Waits for | Advantage | Your decision
0 | Set-up (me) | Fix the shared shapes first: blueprint file, run log, gold table names, memory entry; add every new route and page as an empty stub | app.py, App.tsx, route_permissions.yaml, docs/plan/SHAPES.md | - | Lets the 20 agents below start at the same moment without editing the same files
1 | Intent: wall | Invite panel: join link, seats, revoke | wall/InvitePanel.tsx | 0 | Organiser can bring people in without the old screen
2 | Intent: wall | Organiser stage bar: briefing, open rooms, close, to the wall | wall/StageBar.tsx | 0 | Organiser runs the whole session from the wall
3 | Intent: Define | Charter screen in the new look, signing included | charter/CharterView.tsx | 0 | Sponsor signs the charter in the new product
4 | Intent: baseline | Baseline screen: measures list, status, edit one measure | pages/BaselinePage.tsx | 0 | Owners finish definitions in one screen, not five
5 | Intent: baseline | Baseline sign-off panel | pages/BaselineSignoff.tsx | 0 | Sponsor signs the baseline; room 3 unlocks
6 | Intent: bring | Interview pages in the new look | pages/InterviewPage.tsx (re-skin) | 0 | People answer in the same look as everything else
7 | Intent: wall | Join page and guest private room in the new look | room/JoinPage.tsx (re-skin) | 0 | Guests without accounts get the new look
8 | Agent memory | Memory store: filters, summarise, compact, company digest | sh_platform/memory/ | 0 | Agents learn the company; the next cycle needs less human time
9 | Agent memory | Wire memory into North, Lens, Nira; 'what I remember about you' screen | agent prompt files, pages/MemoryPage.tsx | 0 (shape), 8 to land | People see and correct what agents remember
10 | Build: blueprint | Architect: draft blueprint.json from the signed baseline and plan | sh_platform/build/blueprint.py | 0 | Replaces about a week of a data architect
11 | Build: blueprint | Blueprint screen and sign | pages/BlueprintPage.tsx | 0 | Head of data signs the design in one screen
12 | Build: pipelines | Pipeline contracts and runner: silver and gold, run log | sh_platform/build/runner.py | 0 | Replaces weeks of data engineering
13 | Build: pipelines | Pipelines screen with Run now and the run log | pages/PipelinesPage.tsx | 0 | Admin loads data with one click
14 | Build: data | Demo gold tables for the family office (synthetic) | packs/family_office demo data, seed script | 0 | Consume screens can be built before real loads exist
15 | Build: prove | Prover: recompute each measure from gold, compare with reported | sh_platform/build/prove.py | 0 | Evidence per measure without analyst reconciliation
16 | Build: prove | Prove and release screen with sponsor sign | pages/ProvePage.tsx | 0 | Sponsor releases numbers with the evidence attached
17 | Build: ops | Ops screen over the run log | pages/OpsPage.tsx | 0 | Late or failed loads found before the committee meets
18 | Consume | Consume home and Feeds | pages/ConsumeCentre.tsx, pages/FeedsPage.tsx | 0 | Everyone sees one version of the numbers
19 | Consume | Market forces | pages/MarketPage.tsx | 0 | Market context next to the company's own measures
20 | Consume | What-if | pages/WhatIfPage.tsx, sh_platform/build/whatif.py | 0 | Scenarios in minutes instead of a day in Excel
P1 | Pulse | Pulse route: one read over sessions, baselines, assessments, run log, graph and packs, filtered by viewer; at most seven lines | sh_platform/pulse/ | 0 | The data for every landing page
P2 | Pulse | Pulse page, desktop and phone: four strips, deep links, nothing-needs-you state; becomes the landing page | pages/PulsePage.tsx | 0 | The new front door, as designed on the canvas
P3 | Pulse | Role gates: Build and Ops only for the data team, Control for admins, centres hidden otherwise | shell role rules | 0 | Nobody sees what is not theirs
P4 | Pulse | Nira's drafted messages by email through the gateway: invite, reminder, sponsor ask, daily ops report | sh_platform/pulse/messages.py | 0 | The pulse reaches people where they are
M1 | Map | Map provenance and versions: every node carries which session, who signed, when; a version per change | sh_platform/graph/versions.py | 0 | Source of truth on every thing
M2 | Map | Comments, suggestions and ambiguity flags on a node; routed to the owner's pulse; steward accepts or declines | sh_platform/graph/comments.py, pages/NodePage.tsx | 0 | People make the ontology better; one steward keeps it coherent
M3 | Map | Signed register page: every signed KPI and definition with owner, pipeline, signers, version | pages/RegisterPage.tsx | 0 | Data democratisation: who owns what, in one place
M4 | Map | Pipeline nodes: design, UAT and release signatures and code commits on the map | sh_platform/graph/build_nodes.py | 0 (shape) | Trace how the numbers were built and by whom
R1 | Charter | Build roles named at the charter: architect, developer, tester or UAT sponsor, sponsor, ops, informed | charter contract and screen | 0 | Every hand-over has a named person
R2 | Build | UAT sign-off step between reconcile and release, by the named tester | sh_platform/build/uat.py, ProvePage | 0 | Nothing goes live that the business did not test
Plan | Step 0 by me (about 25 min: shared shapes incl. pulse line, map version, comment, register), then agents 1-20 plus P1-P4, M1-M4, R1-R2 (30 agents) all at once on Sonnet; I review and land each as it finishes, then walk the whole journey once.
Time | About 25 min set-up, about 60-90 min for all 30 builds in parallel, about 15 min per landing as they arrive, then about 2 h for the journey walk and fixes. Roughly 5 hours in total.

## User journey
Step | Stage | Who | Screen and address | What the person does | What they see | State today | Work to do | Package | Build minutes | Why this long | Test | Your decision | Your comment
A1 | Set up | Super admin | Control panel /centre/control | Signs in, opens the Control panel, creates the company, switches the Intent and Build centres on | Company list, centre and module switches | Works in the new look | None | - | 0 | Built (IC-5b) | -
A2 | Set up | Super admin | None (seed file) | Creates the company admin and people accounts | Accounts exist from the seed file data/_control/seed_credentials.txt | Not in MVP | Invite-by-email screen later | - | 0 | Demo uses seeded accounts | -
B1 | Sign in | Company admin | Sign-in page /login | Types email and password | Lands on the Intent centre home | Works in the new look | None | - | 0 | Built (IC-S2) | -
C1 | Intent: start | Company admin | Intent home /centre/intent | Reads the three rooms and the counts | Room 1 lit, rooms 2 and 3 dim until the room before is done | Works in the new look | None | - | 0 | Built (IC-1b, IC-2w) | -
C2 | Intent: bring | Company admin | Bring what you have /centre/intent/bring | Uploads strategy notes, policies, reports into nine tiles | Each tile: read or nothing new; readiness bar; what is still missing | Works in the new look | None | - | 0 | Built (IC-0, IC-S1) | -
C3 | Intent: bring | Company admin | Interviews /company/interview | Sends a short interview link to each key person | Who answered, who has not | Works, old screen only | Re-skin into the new look | W1-D | 15 | Look-only change: same data and calls; copy the page frame used by Bring | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
C4 | Intent: bring | Person interviewed (no account) | Interview by link /interview/:token | Answers questions by text or voice | Thank-you page | Works, old screen only | Re-skin with the link-page frame built tonight | W1-D | 10 | Same as the upload-by-link page done tonight | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
D1 | Room 1: the wall | Company admin (organiser) | Home: Start the wall | Clicks Start the wall; types topic, purpose, days | The wall opens | Works in the new look | None | - | 0 | Built (IC-2t, IC-2x) | -
D2 | Room 1: the wall | Organiser | The wall /centre/intent/wall/:id | Copies the join link and sends it to people | Join link, seats taken or free, revoke a seat | To build | Invite panel on the wall: link, seats, revoke (the routes exist) | W1-A | 25 | Screen only: routes for link, seats and revoke already exist; copy from the old room screen | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
D3 | Room 1: the wall | Participant (no account) | Join by link /join/:code | Opens the link, types name and role, takes a seat | Lands in their private room | Works, old screen only | Re-skin the join page and the guest private room | W1-D | 25 | Look-only change, but two screens (join and the guest room) | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
D4 | Room 1: the wall | Organiser | The wall | Moves the session on: briefing, open the private rooms, close them, bring everyone to the wall | A stage bar with the next step and a confirm | To build | Organiser stage bar on the wall (the stage routes exist) | W1-A | 30 | Screen only: calls existing routes; each step needs a confirm and a plain message | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
D5 | Room 1: the wall | Each participant | North panel on the wall | Answers North's four questions; writes cards; marks anonymous or sealed | Cards appear in four lanes | Works in the new look | None (guests covered by D3) | - | 0 | Built (IC-2a to IC-2h, IC-2p) | -
D6 | Room 1: the wall | Organiser | The wall: projector view | Shows the wall on a big screen | Lanes and counts, no names | Works in the new look | None | - | 0 | Built (IC-2b) | -
D7 | Room 1: the wall | Organiser or the clock | The wall | The wall closes after the chosen days, or the organiser closes it | Wall frozen; North groups cards into clusters; Define unlocks | Works in the new look | Manual close comes with D4 | W1-A | 0 | Counted in D4 | -
E1 | Room 2: Define | Organiser | Define /centre/intent/define/:id | Drags clusters onto Must, Should, Good to have, Future | Shelves with counts and votes | Works in the new look | None | - | 0 | Built (IC-3a, IC-3b, IC-3s) | -
E2 | Room 2: Define | Organiser | Define: Lens panel | Reads each measure's definition; confirms it or sends it back with a note | Definition with its source; governed ring | Works in the new look | None | - | 0 | Built (IC-3e) | -
E3 | Room 2: Define | Sponsor | Charter (old screen under /modules/m1_intent) | Reads the charter (what we want to know, why, which measures) and signs | Signed charter; download | Works, old screen only | Charter screen in the new look, reached from Define | W1-B | 30 | Copy the old charter screen; re-skin; one link from Define and from home | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
E4 | Room 2: Define | Analyst or data owner | Baseline catalogue (old screens under /modules/m2_baseline) | Completes each Must and Should measure: business meaning, calculation, source, period | Catalogue with the gaps shown | Works, old screen only | Baseline screen in the new look: list of measures, status, open one to edit | W1-C | 45 | Biggest gap: five old screens (catalogue, glossary, governance, requests, sign-off) folded into one; copy their forms | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
E5 | Room 2: Define | Data owner (no account) | Owner question by link /answer/:token | Answers a question about their measure | The answer goes back to the catalogue | Works in the new look | None | - | 0 | Built tonight (IC-M3G) | -
E6 | Room 2: Define | Sponsor | Baseline sign-off (old screen) | Signs the baseline when every Must measure is governed | Signed baseline; room 3 unlocks | Works, old screen only | Sign-off panel on the new Baseline screen | W1-C | 15 | Copy the old sign-off panel into the new screen | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
F1 | Room 3: Moment of truth | Company admin | Home: Start the moment of truth | Starts the trial | The Truth screen opens | Works in the new look | None | - | 0 | Built (IC-4b) | -
F2 | Room 3: Moment of truth | Company admin | Data request /centre/intent/truth/:id/request | Asks each source owner for a sample file by link | Sources as cards: asked, received, profiled | Works in the new look | None | - | 0 | Built (IC-M3U) | -
F3 | Room 3: Moment of truth | Source owner (no account) | Upload by link /intake/:token | Uploads the sample file | Received; nothing else of the company is shown | Works in the new look | None | - | 0 | Built tonight (IC-M3G) | -
F4 | Room 3: Moment of truth | Company admin, sponsor | Truth screen | Reads the trial: computed versus reported figure per measure; quality rules | MATCH, GAP or NOT YET; fixes in amber | Works in the new look | None | - | 0 | Built (IC-4a, IC-0d) | -
F5 | Room 3: Moment of truth | Sponsor | Truth screen: plan | Reads the plan in three bands and signs it | Signed plan; the Build centre can start | Works in the new look | None | - | 0 | Built (IC-4b) | -
F6 | Intent: results | Sponsor | Outcomes /centre/intent/outcomes | Sees progress numbers | Sessions, cards, measures governed, trials matched | Works in the new look | None | - | 0 | Built (IC-6a) | -
F7 | Intent: results | Sponsor | Company graph /centre/intent/graph | Sees who owns which measure and which measures have no source | Map, trace per measure, holes | Built, not committed | Commit it (step 0) | Step 0 | 10 | Code done and leak fixed; one test file to fix | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
G1 | Build: start | Company admin | Build home /centre/build | Opens the Build centre | Three rooms; room 1 lit | Works in the new look | None | - | 0 | Built (BC-1) | -
G2 | Build room 1: Architect | Company admin (head of data) | Environment /centre/build/environment | Confirms five answers: where the warehouse lives, existing warehouse, scheduler, where files arrive, where alerts go | Each answer with its source; Confirm | Works in the new look | None | - | 0 | Built (BC-1) | -
G3 | Build room 1: Architect | Company admin (head of data) | Blueprint /centre/build/blueprint | Reads the drafted data model: tables, keys, each measure's lineage, rules, who may see, schedule; signs | Blueprint with a source for every line; Sign | To build | Architect drafts blueprint.json from the signed catalogue and plan; screen; sign | W2-A | 60 | New logic: map catalogue measures to facts and dimensions; copy model drafting from the earlier repo | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
G4 | Build room 2: Build | Company admin | Pipelines /centre/build/pipelines | Reads one card per source: where files land, when expected, which checks run | One pipeline per source, from the blueprint | To build | Pipeline contract per source generated from the blueprint; list screen | W2-B | 40 | New: the contract file and its screen; inputs come from G3 | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
G5 | Build room 2: Build | Company admin | Pipelines: Run now | Clicks Run now on a source | Run log: rows loaded, checks passed or failed, time taken | To build | Runner: bronze (exists), silver, gold marts; run log; Run now button | W2-B | 60 | Copy the silver and gold transforms from the earlier repo; the DuckDB warehouse exists (BC-4) | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
G6 | Build room 2: Build | Company admin, owners | Prove /centre/build/prove | Reads each measure recomputed from the warehouse versus the reported figure | Match, or gap with a reason, per period | To build | Prover: recompute per measure; evidence per measure | W3-A | 45 | Reuses the trial comparison from room 3, on loaded data | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
G7 | Build room 2: Build | Sponsor | Prove: Release | Signs the release when every measure matches or has an accepted gap | Release signed; data marked live | To build | Release panel and sign-off | W3-A | 20 | Copy the release sign-off from the earlier repo | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
G8 | Build room 3: Ops | Company admin, owners | Ops /centre/build/ops | Checks today's loads: on time, late, failed, who must act | One list per day | To build | Ops screen over the run log | W3-B | 30 | Screen over the run log written by G5 | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
H1 | Consume: start | Sponsor, owners | Consume home /centre/consume | Opens the Consume centre | Three rooms: Feeds, Market forces, What-if | To build | Home page and top-bar link | W2-C | 15 | Copy of the Build home | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
H2 | Consume: Feeds | Sponsor, owners | Feeds /centre/consume/feeds | Reads each governed measure: latest value, trend, owner | Measure cards; restricted ones only for the people listed | To build | Feeds screen reading the gold marts | W2-C | 45 | New screen; needs gold marts from G5 (demo marts seeded first so it does not wait) | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
H3 | Consume: Market forces | Sponsor | Market forces /centre/consume/market | Reads industry briefs and signals next to the company's own measures | Briefs from the family office pack, labelled as outside material | To build | Screen over the pack's market briefs and signals | W2-D | 35 | Copy from the earlier repo; the pack content already exists | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
H4 | Consume: What-if | Sponsor | What-if /centre/consume/what-if | Changes one driver by a percentage | Which measures move and by how much, with the path | To build | Driver list from the graph; simple recalculation | W3-C | 60 | New logic; one driver at a time | Builder: 2 to 4 tests for this step only. Me: click through once as this person.
Z1 | Check | Me | Whole journey | Runs A1 to H4 on the demo company as each person | A list of what broke | To do | One click-through per wave; the full run after wave 3 | W4 | 120 | Click-through by hand, not automated suites | Builder: 2 to 4 tests for this step only. Me: click through once as this person.

## Build waves
Package | What | Journey steps | Agents | Minutes (build, land, click-through) | Note | Your decision
Step 0 | Commit the company graph | F7 | 0 | 10 | Me
W1-A | Wall: invite panel and organiser stage bar | D2, D4, D7 | 1 | 55 | Screen only, over existing routes
W1-B | Charter in the new look | E3 | 1 | 30 | Copy and re-skin
W1-C | Baseline in the new look (catalogue and sign-off) | E4, E6 | 1 | 60 | Largest Intent gap
W1-D | Link pages and interviews in the new look | C3, C4, D3 | 1 | 50 | Look-only
W2-A | Blueprint | G3 | 1 | 60 | New logic plus a screen
W2-B | Pipelines and Run now | G4, G5 | 1 | 100 | New runner; copies the earlier transforms
W2-C | Consume home and Feeds | H1, H2 | 1 | 60 | Uses seeded demo gold marts
W2-D | Market forces | H3 | 1 | 35 | Copy
W3-A | Prove and release | G6, G7 | 1 | 65 | Needs G5
W3-B | Ops | G8 | 1 | 30 | Needs G5
W3-C | What-if | H4 | 1 | 60 | Needs the graph and the marts
W4 | Whole journey click-through and fixes | Z1 | 0 | 120 | Me, plus one fixer agent if needed
Wave 1 (4 agents at once) |  |  |  |  | Parallel: the longest package sets the time
Wave 2 (4 agents at once)
Wave 3 (3 agents at once)
Step 0 and wave 4
Total minutes to MVP

## Not in MVP
Item | Why later
Full automated test suite (about 3,500 tests) | Runs after the MVP works end to end
Security review | After the MVP, before any real client
Invite people by email | Seeded accounts are enough for the demo
Scan an existing warehouse | The demo company has none
Airflow | The built-in runner is enough
Slack and Teams messages | The Ops screen is enough for the demo
Define across several walls | One wall per demo